## Sheet1
BVK group web site development finding
Sr. No | Section (Page for reference) | Description | Note | Date of Completion | Date of Testing | Assigned to | Status Of Dzone as on 01st Mar 21 | WMW remarks after checking As on 4th Mar 21 | Dzone Comments | WMW Remarks / Observation On 5th Mar 21 | WMW Remarks / Observation On 11th Mar 21 | WMW Remarks / Observation On 15th Mar 21 | WMW Remarks / Observation On 17th Mar 21 | Remarks By Dzone India (24-03-2021) | WMW Remarks / Observation On 30th Mar 21 | Action plan after meeting of 01 Apr 2021 | Status as on 12 Apr 2021 | 1
1 | Home Page | Text display on banner should be dynamic , facility to change through control panel required http://dzoneist.com/bvklive/ |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Not as required and explain, Multiple text display on single banner, text entry facility should be separate | As per your explanation its is a change request and need to discuss with Dayal Sir | Text and image to be separate and text editing facility required | Text and image to be separate and text editing facility required | Ok | Ok | Done | Done
2 | Home Page | Multiple text display facility required http://dzoneist.com/bvklive/ |  | 25-02-2021 | 26-02-2021 | Designing Team | Done | [6 empty] | Done | Done
3 | Home Page | Message to use ' third-party website tracking technologies….' should come only one time at start page of web site browsing process for a person http://dzoneist.com/bvklive/ |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Message not display on first page | It was not an issue, you have checked this | Correction done , but have following issue / problem 1. Double click 2. Once for every unique IP address for each browsing session | Correction done , but have following issue / problem 1. Double click 2. Once for every unique IP address for each browsing session | correction done but still it is required double click on accept button which should be single click |  | Done | Done
4 | Home Page | Till the user not accept our ' third party website tracking technologies…' message , he should not be able to brows any page http://dzoneist.com/bvklive/ |  | 23-02-2021 | 24-02-2021 | Development Team | Done | [6 empty] | Done | Done
5 | All | Browser and browser version compatibility should be applicable | It's already compatible to all browsers. It will not work properly on old version due to up gradation of technology | [5 empty] | Website will not work on older version browsers as the technology conflicts occurs | technical solution required | technical solution required | Menu type change when we Open in Microsoft edge |  | Done | Done
6 | control panel | Concept of separate upload of ‘Title’ and ‘content’ which is available on product page will be applied on every page of website (where ever required) Example page :http://dzoneist.com/bvklive/our product Applied to : all other page like http://dzoneist.com/bvklive/about-block | In block section title and description will be separate | 23-02-2021 | 24-02-2021 | Development Team | Done | Not done in all page | As per our discussion it will be resolved from our end | Will resolved by Dzone | Changes done but Not showing title when we edit title in block 2 and block 3 | Not showing title when we edit title in block 2 and block 3 | Done , But to be check underline of block 2 title | Done | Done
7 | control panel | Spelling of title to be correct 'Titile' http://dzoneist.com/bvklive/ourproduct |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Ok |  | Ok | Done | Done | Done | Done | Done
8 | control panel | Option to change following should be available in all page where any dynamic Image / content uploading facility is given (If not match standard then should not be upload) http://dzoneist.com/bvklive/ourproduct |  | 24-02-2021 | 25-02-2021 | Development Team | Done |  |  | configuration based upload facility required | Range / configuration based upload facility required | Range / configuration based upload facility required |  | Done | Done
9 | control panel | 1. Image size 2. Image resolution 3. Font size 4. Font Color |  | 24-02-2021 | 25-02-2021 | Development Team | Done | [6 empty] | Done | Done
10 | control panel | All image uploaded in website should be available in one central location with identification where the particular image is uploaded |  | 24-02-2021 | 25-02-2021 | Development Team | Done |  |  | Done | Done | Done | Done | Done | Done
11 | control panel | Active /Deactive option and sequence change option for any section , Page, Menu required |  | 24-02-2021 | 25-02-2021 | Development Team | Done | Not done |  | Will resolved by Dzone | Option provided page level but for menu this option is not available, in some page deactivate done by admin but those item is also shown when use brows the page | Block 3 1. Not Able to Add new photo 2. Active /Deactive not working | done | Done | done
12 | control panel | Option to upload Video file and upload link of YouTube and Vimeo required |  | 24-02-2021 | 25-02-2021 | Development Team |  |  |  | Not done | Not done | Video upload facility not available in block 2,Block 3, Block 4,Our Product Note : Type selected Video but system allowed to upload image | Video upload facility not available in block 2,Block 3, Block 4,Our Product Note : Type selected Video but system allowed to upload image | Done | Facility on CMs page to upload video |  | Facility on CMs page to upload video | 1
13 | All | Search button not working, it should be active and will search in full website |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Not working | As per our discussion you need this on all steps and it will be resolved from our end | Will resolved by Dzone | Done | Showing result but when we click on link of search it is showing error (Should open the link page) | Showing result but when we click on link of search it is showing error (Should open the link page) | Done | Done
14 | All | Mail option should available with link\path in mail (From which page this mail is created ) | Subject in mail | 23-02-2021 | 24-02-2021 | Development Team | Done | mail to be generate with local available mail solution | This option has been implemented as per the standards | mail to be generate with local available mail solution | mail to be generate with local available mail solution | done | done | Done | Done
15 | Control panel | Process to link a page with menu | Already | Already Available | Already Available | Development Team | Done |  |  | Done | Done | Done | Done |  | Done
16 | Home Page | Menu or sub menu landing page should be active as per our requirement i.e. if a page is link on sub menu item then it should be open other wise its upper level menu page should be open |  | 25-02-2021 | 26-02-2021 | Designing Team | Done |  |  | Will resolved by Dzone | Done , as there are so many same pages uploaded during testing , so final testing will be done when actual data upload | Done , as there are so many same pages uploaded during testing , so final testing will be done when actual data upload | Done , as there are so many same pages uploaded during testing , so final testing will be done when actual data upload | Done | Done
17 | control panel | Page content is not editable (active / deactive option is also required) http://dzoneist.com/bvklive/view-pages |  | 24-02-2021 | 25-02-2021 | Development Team | Done |  |  | OK | Done | Done | Done | Done | Done
18 | All | User page visit location in site to be shown (Breadcrumbs) |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Not working properly | Will be resolved from our end | Will resolved by Dzone | Modification done but not working properly | Done But showing wrong path | Done But showing wrong path | Done | Done
19 | control panel | Fields on job page should be dynamic (Admin should be able to add or remove new column) | Not feasible , you can tell us all possible fields which we will add and thpse fields will not be mandatory | [5 empty] | Not feasible | ? | Modification done but have following issue : 1. Company logo to be shown to user when they brows the page 2. Editing in job post required at control panel 3. Job page formatting (Few details not shown on job page) 4. filter on job page to be check 5. Search facility on inner page of job is not required 6 inactive job should not be available to end user | Filter given but it is not working properly 1. showing all active and deactive jobs 2.View button not working 3.Logo Not Showing | Filter given but it is not working properly Title for following is required 1.Description Content 2. Responsibility Control Panel screen of job page to be rearrange | Done | Done
20 | control panel | Mail account configuration for job applied information | Already available | Already available | Already available |  | Done |  | Text editor is not working that’s why you are getting issue. It will be resolved from our end | Will resolved by Dzone |  | How to add mail a/c of recipient | How to add mail a/c of recipient | Done | Not Possible as per dzone | Accepted by Dzone, to complete this task | Done, Mail configuration facility given but Mail received or not at configured a/c to be checked2 | 1
21 | Home Page | Footer page image (Map) to be remove |  |  |  | Development Team | Done | Ok |  | Ok | Done | Done | Done |  | Done
22 | control panel | Option to manage home pager footer option (footer menu) and link page of footer menu should be dynamic/ customizable |  | 25-02-2021 | 26/2/2021 | Development Team | Done |  |  | Editing facility / Page order facility not available | Editing facility / Page order facility not available | Editing facility / Page order facility not available | Editing facility / Page order facility not available | Done | Done
23 | control panel | My BVK Link/ Option required https://www.tetrapak.com/solutions |  | Will be done in next phase |  | Development Team | [7 empty] | Not Possible | Not Possible as per dzone |  | Landing Page to be Developed | 1
24 | Home Page | Disclaimer for web page cookies to be shone |  | 23-02-2021 | 24-02-2021 | Development Team | Done |  |  | Ok, but Disappear to be done | Msg shown but disappearing to be done | Done | Done | Done | Done
25 | Home Page | Copyright message should be editable by admin |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Editing Facility not available | It is dynamic. But as per your requirement it needs a discussion | Full text editing required | Full text editing required | Done | Done | Done | Done
26 | Home Page | "Home" tab to be remove from home page menu |  |  |  |  | Done | Ok |  | Ok | Done | Done | Done | Done | Done
27 | Home Page | My BVK Link page login should be integrate with AD and user login should authenticate https://www.tetrapak.com/solutions |  |  |  |  | Our of Scope |  | Out of Scope | ? | ? |  | Ravnish ji | Not Possible | Not Possible as per dzone |  | Landing Page to be dev eloped | 1
28 |  | Facility to change page wise image for theme level | [9 empty] | Modification done but not working i.e. insight page | Done | Done | Done
29 |  | Filter on job page on ,Company,Funcation,Location,Level | [8 empty] | Have some issue as written in point no 19 | Have some issue as written in point no 19 |  | Done | Done
30 |  | Facility to upload company wise logo at every job | [8 empty] | Have some issue as written in point no 19 | Have some issue as written in point no 19 |  | Done | Done
31 |  | As per dzone point no 19 is (related to add new column on job page) Not feasible, to resolve this we can change the layout of page from vertical to horizontal display | [8 empty] | Have some issue as written in point no 19 | Have some issue as written in point no 19 |  | Done | Done
32 |  | Mail from web site as per sample mail sent to dzone | [11 empty] | Done | ?? |  |  | 1
33 |  | Facility to Hyper link on menu | [11 empty] | Not Possible | done
34 |  | Embed Hyper link on picture of product page | [11 empty] | Done | Not Possible as per dzone | Accepted by Dzone, to complete this task | Done
35 |  | how to edit contact page | [11 empty] | Done | Done
36 |  | Blog page not showing all active page / image not coming in internal page | [11 empty] | Done | Done
37 |  | Email for contact page to be configurable | [12 empty] | Not Possible as per dzone | Accepted by Dzone, to complete this task | Done, Mail configuration facility given but Mail received or not at configured a/c to be checked2 | 1
38 |  | Link page on block 1 to bloc 4, Our product, articles etc | [12 empty] | Not Possible as per dzone | Accepted by Dzone, to complete this task | Done
|  | Email template to be configured | [12 empty] | Done
|  | Logo position in job page center align | [14 empty] | Done
|  | Footer menu test change page and footer menu page dropdown in control panel should be link | [13 empty] | Accepted by Dzone, to complete this task | Done
|  | Social media link Active/ Deactive facility required | [12 empty] | Done
|  | hero image on job page/ articles / news /contact/ blog | [13 empty] | Accepted by Dzone, to complete this task | Done
|  | Facility to change master logo | [14 empty] | Done
|  | Contact page to be dynamic (Full Page content editing facility required) | [12 empty] | Part Content editing facility done | Accepted by Dzone, to complete this task | Contact page to be design as per concept given in seprate file | 1
|  | Product page edit , image field required which should not be | [13 empty] | Accepted by Dzone, to complete this task | Done
|  | Article image gets remove when we edit the article post showing some problem when we click onimage to tra | [14 empty] | Done
|  | Main Header title of Product , News and Articles to be configrable | [14 empty] | Configrable heading required | 1
|  | Contact heading to be change | [14 empty] | Contact Page Heading not changing
View all button not working on product, news, articles, blog section of home page
CMS page (Template one) is not working properly as per the designee , Page link to be activated
News, Blog, Article on CMS page should be comer as per requirement and content of these block should be as per page relation