## Sheet1
BVK group web site development finding as on 17 Feb 2021
Sr. No | Section (Page for reference) | Description | Note | Date of Completion | Date of Testing | Assigned to | Status Of Dzone as on 01st Mar 21 | WMW remarks after checking As on 4th Mar 21
1 | Home Page | Text display on banner should be dynamic , facility to change through control panel required http://dzoneist.com/bvklive/ |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Not as required and explain, Multiple text display on single banner, text entry facility should be separate
2 | Home Page | Multiple text display facility required http://dzoneist.com/bvklive/ |  | 25-02-2021 | 26-02-2021 | Designing Team | Done
3 | Home Page | Message to use ' third-party website tracking technologies….' should come only one time at start page of web site browsing process for a person http://dzoneist.com/bvklive/ |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Message not display on first page
4 | Home Page | Till the user not accept our ' third party website tracking technologies…' message , he should not be able to brows any page http://dzoneist.com/bvklive/ |  | 23-02-2021 | 24-02-2021 | Development Team | Done
5 | All | Browser and browser version compatibility should be applicable | It's already compatible to all browsers. It will not work properly on old version due to upgradation of technology
6 | control panel | Concept of separate upload of ‘Title’ and ‘content’ which is available on product page will be applied on every page of website (where ever required) Example page :http://dzoneist.com/bvklive/our product Applied to : all other page like http://dzoneist.com/bvklive/about-block | In block section title and description will be separate | 23-02-2021 | 24-02-2021 | Development Team | Done | Not done in all page
7 | control panel | Spelling of title to be correct 'Titile' http://dzoneist.com/bvklive/ourproduct |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Ok
8 | control panel | Option to change following should be available in all page where any dynamic Image / content uploading facility is given (If not match standard then should not be upload) http://dzoneist.com/bvklive/ourproduct |  | 24-02-2021 | 25-02-2021 | Development Team | Image Size Validation os alrready available
9 | control panel | 1. Image size 2. Image resolution 3. Font size 4. Font Color |  | 24-02-2021 | 25-02-2021 | Development Team
10 | control panel | All image uploaded in website should be available in one central location with identification where the particular image is uploaded |  | 24-02-2021 | 25-02-2021 | Development Team
11 | control panel | Active /Deactive option and sequence change option for any section , Page, Menu required |  | 24-02-2021 | 25-02-2021 | Development Team | Done | Not done
12 | control panel | Option to upload Video file and upload link of YouTube and Vimeo required |  | 24-02-2021 | 25-02-2021 | Development Team
13 | All | Search button not working, it should be active and will search in full website |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Not working
14 | All | Mail option should available with link\path in mail (From which page this mail is created ) | Subject in mail | 23-02-2021 | 24-02-2021 | Development Team | Done | mail to be generate with local available mail solution
15 | Control panel | Process to link a page with menu | Already | Already Available | Already Available | Development Team
16 | Home Page | Menu or sub menu landing page should be active as per our requirement i.e. if a page is link on sub menu item then it should be open other wise its upper level menu page should be open |  | 25-02-2021 | 26-02-2021 | Designing Team | Pending from Arjun End
17 | control panel | Page content is not editable (active / deactive option is also required) http://dzoneist.com/bvklive/view-pages |  | 24-02-2021 | 25-02-2021 | Development Team
18 | All | User page visit location in site to be shown (Breadcrumbs) |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Not working properly
19 | control panel | Fields on job page should be dynamic (Admin should be able to add or remove new column) | Not feasible , you can tell us all possible fields which we will add and thpse fields will not be mandatory
20 | control panel | Mail account configuration for job applied information | Already available | Already available | Already available
21 | Home Page | Footer page image (Map) to be remove |  |  |  | Development Team | Done | Ok
22 | control panel | Option to manage home pager footer option (footer menu) and link page of footer menu should be dynamic/ customizable |  | 25-02-2021 | 26/2/2021 | Development Team
23 | control panel | My BVK Link/ Option required https://www.tetrapak.com/solutions |  | Will be done in next phase |  | Development Team
24 | Home Page | Disclaimer for web page cookies to be shone |  | 23-02-2021 | 24-02-2021 | Development Team | Pending from Arjun End
25 | Home Page | Copyright message should be editable by admin |  | 23-02-2021 | 24-02-2021 | Development Team | Done | Editing Facility not available
26 | Home Page | "Home" tab to be remove from home page menu | [5 empty] | Ok
27 | Home Page | My BVK Link page login should be integrate with AD and user login should authenticate https://www.tetrapak.com/solutions