## Sheet1
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Super Admin (Owner)
Login Panel
Admin Manager
Product Manager
Dynamic Brand Manager
Coupon/Discount Manager
Customer Manager
Customer Order Manager
Custom Reports Manager (Exports in Excel and Pdf)
Country wise Currency Manager (Paid Api)
Page Manager
Feedback Manager
Manage Profile
Admin
Login Panel
Admin Manager
Product Manager
Dynamic Brand Manager
Coupon/Discount Manager
Customer Manager
Customer Order Manager
Custom Reports Manager (Exports in Excel and Pdf)
Country wise Currency Manager (Paid Api)
Page Manager
Feedback Manager
Manage Profile
Customer
Login Screen
Signup process (approval basis)
login id/pass through email (admin panel)
Approval request can be approved or rejected by admin
Gallery image
My Account complete functionality
Recently viewed product
Notification on Gmail and Mobile
Wallet Amount Redemption (Virtual Money)
Search items based on (item name, Sku no., Price, latest collection)
Detailed view of item
Place order
My Orders
Edit order
Cancel order
Past orders (complete orders history)
Order detailed view
Mnage Profile
Customer Check Out
Search product name
search from sku number
Keyword Search
Product Search by Brand & Category options
Site other Content Search
Product Filter with Instant listing
Browse/Filter Products listing by Category
Export Catlog in PDF/Excel
Advance Requirements
17 Advance Requirements
* 360 View Detail
Resource Details | No. 0f Resources | Man Hours | Charge per hours | Total Efforts
| 6 | 672 | 4032 | 500000
UI Developer | 1 | 820 | 100 | 82000
Data Base developer | 1 | 610 | 100 | 61000
Node Developer | 1 | 950 | 300 | 285000
React/Angular developer | 1 | 950 | 100 | 95000
Project Manager/ Lead | 1 | 400 |  | 0
Tester/ Reasercher | 1 | 302 | 50 | 15100
|  | Expected Price |  | 538100
Grand Total(Hrs) | Total Hours | Rate of Development | Total Cost
| 4032 | 124 INR | 500000
Total Final Cost | 50000
Payment Breakup | Amout to be released | Expected-Recived | Amout to be paid
UI Layout Finalization (up to 30% ) | 30% of Final Amount | 150000-50000 | 100000
Data Base Schema (up to 20% )
Backend Development(upto 25%)
UI Layout Finalization (up to 90% ) | 30% of Final Amount | 150000-0 | 150000
Data Base Schema (up to 80% )
Backend Development(upto 60%)
UI Layout Finalization (up to 100% ) | 30% of Final Amount | 150000-0 | 150000
Data Base Schema (up to 100% )
Backend Development(upto 100%)
UI Layout Testing & Bug Fixing | 10% of Final Amount | 50000-0 | 50000
Data Base Schema Testing & Bug Fixing
Backend Development Testing & Bug Fixing
* Total Fee quoted is exclusive of GST
Expected Delivery 07 June 2021
Modular Testing Start
Small Pending Work and Bug Fixing
Milestone 1
Milestone 2
Milestone 3 3
Milestone 4 3